## Slide 1: Sprint 04
Team 01

## Slide 2: Overview
Team Roles
Sprint 04 Goals
Task Difficulty Breakdown
Live Kanban Board Review
Demo’s (Cloud, Site, Team)
Completed Task Summary
Tasks Pushed
Summary
Conclusion

## Slide 3: Team Roles
Project Manager: Greg Eure
IT Orchestration and Security: Armani Lesure
Developer: Tenzin Choeying
Developer: Phallyn Habercoss
Developer: Drew Snarski

## Slide 4: Sprint 04 Goals
Integrate deployment to the required cloud environment (required)
Pre-populate the database (required)
Update the ERD to meet Django requirements
Modify the website look & feel to match the UI/UX design
Secure the MariaDB database and implement Fail2Ban intrusion detection

## Slide 5: Task Difficulty Points Breakdown
Cloud environment integration/deployment: 5 points
Implement database security: 1 point
Implement Fail2Ban intrusion detection: 1 point
Prepopulate test users & q/a: 1 point
Export/import database containing pre-population: 2 points
Modify ERD to match actual database (after Django modifications): 2 points
Modify home page to match UI/UX: 5 points
Modify profile page to match UI/UX: 5 points
Modify question/answer page to match UI/UX: 3 points
Total: 25 points

## Slide 6: Live Kanban Board Review

## Slide 7: Live Cloud Deployment Demo

## Slide 8: Live Site Demo

## Slide 9: Team Member Demos

## Slide 10: Completed Tasks
Cloud environment integration with existing scripts and deployment of same
Pre-populated the database with 5 test users and required sets of questions/answers
Home page function & design
  Resolved design (color, positioning) issues, altered some text
  Corrected menu functions to work correctly
User profile page functionality
  Needed Admin to create profile (can this be linked to user registration in next sprint?)
  Button functionality corrected (previously didn’t work)
Question/Answer function & design
  Resolved design (color, positioning) issues, altered some text
  Created Cancel function (button)
Updated the ERD

## Slide 11: Completed Tasks: ERD Update

## Slide 12: Tasks not Completed (Pushed to next Sprint)
Implement database security
Implement Fail2Ban intrusion detection

## Slide 13: Summary
Team Roles
Sprint 04 Goals & Points Breakdown
Kanban Board Review
Cloud & Website Demo’s
Completed/Uncompleted Task Review

## Slide 14: Conclusion / Lessons-Learned
Cloud integration was challenging, requiring lots of troubleshooting/problem isolation.
  Lesson-learned: start early as this task takes several days
  Lesson-learned: don’t hard-code IP’s in the scripts or config files
Some tasks may take collaboration across the team to resolve
  Lesson-learned: lean on your teammates for their expertise and insights; escalate issues before they become problems

## Slide 15: Task Overview: Database Security & Fail2Ban
Database Security
Implement MariaDB built-in mysql_secure_installation script, using silent installation methods
Basic security measure to prevent unauthorized database intrusions
Fail2Ban
Open-source intrusion detection software
Attempts to prevent intrusions by identifying failed login attempts and banning the associated IP addresses via dynamic firewall rules